## Product Backlog
User Story Description | MOSCOW | Dependency | Assignee | Status
As a data engineer, I want to collect and preprocess transaction data so that it can be used for model training. | Must Have | Dataset availability | Backend Team | Completed
As a data scientist, I want to train an ML model that predicts fraudulent transactions using historical data. | Must Have | Cleaned data | Backend Team | Completed
As an AI developer, I want to integrate an LLM to provide human-readable explanations for fraud predictions. | Should Have | Trained model | Backend Team | Completed
As a frontend developer, I want to create an interactive dashboard that displays transaction risk results and performance metrics. | Must Have | APIs ready | Frontend Team | Completed
As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | Could Have | Backend & frontend integration | Both Teams | Completed
Note on C1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
|  |  | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend1 | Data Collection | Done | 6 | bar: Day 1 to Day 2
Backend2 | Data Cleaning | Done | 10 | bar: Day 2 to Day 4
Backend3 | Model Training | Done | 12 | bar: Day 3 to Day 6
Backend4 | AI Integration | Done | 8 | bar: Day 4 to Day 6
Frontend1 | UI Development | Done | 10 | bar: Day 5 to Day 8
Both Teams | Deployment | Done | 8 | bar: Day 6 to Day 9
Note on D2: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on E2: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on F2: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on G2: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on H2: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on I2: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on J2: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on K2: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on L2: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on M2: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on N2: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on O2: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on P2: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on Q2: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on R2: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 3 | ML model taking too long to train due to large dataset | Reduced features and applied stratified sampling
Sprint 2 | Day 4 | API returning 500 error during prediction | Debugged endpoint, fixed missing JSON key
Sprint 3 | Day 2 | LLM responses too long and inconsistent | Applied temperature control and prompt optimization
Sprint 4 | Day 1 | Frontend not fetching data due to CORS issue | Enabled CORS in Flask backend

## Retrospection
Start Doing | Stop Doing | Continue Doing | Action taken
Document preprocessing steps clearly | Rushing into training without validation | Collaborating during data cleaning | Created shared preprocessing document
Use version control for model files | Using large data without sampling | Testing each version before training | Implemented model versioning
Write prompts clearly for LLM | Using unstructured prompts | Evaluating prompt output for accuracy | Finalized best-performing prompts
Prepare documentation parallelly | Waiting till the end to test integration | Regular cross-team syncs | Weekly integration meetings scheduled